## Sheet1
No. | Date | Status | Description | More Data
1 | 2009-08-09 | open | found the PSS named directory in the subdirectory where the hour should have been. Possibly the 0th hour was resulting in a blank when forming the directory string in PATHS. Changes the formating. Have not tested.
2 | 2009-08-10 | open | file missing, search tool gets IO exception when clicking on result table entry: 2009/8/1/13/David-PC17/channel 0/2009_08_01_13_32_17_3010.jpg
3 | 2009-08-11 | closed | the app FE LPR Monitor tital bar text is out of date(says First Evidence Control Center)
4 | 2009-08-13 | open | jpegs are getting recorded at a rate of 10 to 15 fps, should be closer to 30 fps
5 | 2009-08-13 | open | jpegs are not always played back in the correct order. Need to implement a correct sorter
6 | 2009-08-14 | open | add a version string to the health statistics for display on the remote monitor
7 | 2009-08-14 | open | add a current time to health stats so monitor can see changes and know the connection and server are alive
8 | 2009-08-14 | open | occasionally get random chars for plate string
9 | 2009-08-14 | open | need to adjust motion detection pixel diff delta, not sensitive enough currently, need a UI setting control for pixel delta and percentage screen
10 | 2009-08-21 | open | the display of the last plate read under the live video display is frozen, but the health status display does show the last plates read.
11 | 2009-08-21 | open | on the XP machine, the service controller and the service itself look in two different places for the user.config file
12 | 2009-08-21 | open | in the search tool, dump all in range does not update the status/progress indicators
13 | 2009-08-22 | open | need to add rotation adjustments to the LPR editor
14 | 2009-08-22 | open | need to add a quick-check health status monitor to the Service Controller